## sheet 1
Decentralized Capital Budget Programme - 2017 - (With Nitonal list)
Pysical and Financial Progress of the month of 2017.12.31
Divisiuonal Name :- Panduwasnuwara West
Secretariat No :- 1281
| SN | Name of MP | Name of Project | GN division |  | Type of Project(Construction /Goods & services) |  | Total Estimate Cost (Rs.) |  | Allocation (Rs) | Expenditure (with Administrative Cost) | Unit of Measure | Physical Progress | [9 empty] | No of Beneficiaries | Remarks
|  |  |  | Name | No | [7 empty] | A | B |  |  |  | C | D | E | F | G
[6 empty] | Construction | Goods & services | With VAT | Witout VAT |  |  |  |  | B1 | B2 | B3 | B4 | [13 empty] | පරිපාලන වියදම්
| WS | Rural Water supply
1 |  | Hon.Minister Dayasiri Jayasekara | Supply water facilities to Meegahmulawaththa village | Hettipola | 1336 | 1 |  |  | 99797.42 | 100000 | 97890.7 | [10 empty] | 1 | 35 |  | 98890.7 | 1000 | 1500 | 2109.3 | 3000 | -890.7 | 1500 | 1468.3605 | 31.6395
|  | Sub Total |  |  | 1336 | 1 |  |  | 99797.42 | 100000 | 97890.7 | [10 empty] | 1 | 35 | [6 empty] | 0 |  |  | 0
| EL | Rural Electrisity | [27 empty] | 0 |  |  | 0
1 |  | Hon. M.P. Thushar Indunila Amarasena | Supplying Electricity to Ran kekulu pre school at Pahala Malagane | Kurundu Kumbura | 1338 | 1 |  |  | 18846.8 | 20000 | 19146.8 | [10 empty] | 1 | 20 |  | 19446.8 | 300 | 300 | 853.2 | 600 | 253.2 | 300 | 287.202 | 12.798
2 |  | Hon.Minister Indika Bandaranayake | Supplying electricity to Rittadeniya society hall | Rittadeniya | 1312 | 1 |  |  | 30626 | 30000 | 29481.8 | [10 empty] | 1 | 25 |  | 29931.8 | 450 | 450 | 518.2 | 900 | -381.8 | 450 | 442.227 | 7.773
3 |  | Hon. M.P. Thushar Indunila Amarasena | Supplying Electrycity for Krandawa Grama Lekam Karyalaya | Karandawa | 1425 | 1 |  |  | 18846.8 | 22500 | 19184.3 | [10 empty] | 1 | 848 |  | 19521.8 | 337.5 | 337.5 | 3315.7 | 675 | 2640.7 | 337.5 | 287.7645 | 49.7355
|  | Sub Total |  |  | 4075 | 3 |  |  | 68319.6 | 72500 | 67812.9 | [10 empty] | 3 | 893 | [9 empty] | 0
| RA | Rural Access | [30 empty] | 0
1 |  | Hon.Minister Dayasiri Jayasekara | Developing remaining part pf the road from near Wendesiwatta Kalyani theater hall to Mr. Mainda's house | Dolohomuna | 1337 | 1 |  |  | 199904.25 | 200000 | 197000 | [10 empty] | 1 | 60 |  | 200000 | 3000 | 3000 | 3000 |  |  | 3000 | 2955 | 45
2 |  | Hon.MP. Mahinda Rajapaksa | Developing Ganegama Dewala Road | Ganegama |  | 1 |  |  | 300409.63 | 300000 | 293500 | [10 empty] | 1 |  |  | 296000 | 2500 | 4500 | 6500 |  |  | 4500 | 4402.5 | 97.5
|  | Sub Total |  |  |  | 2 |  |  | 500313.88 | 500000 | 490500 | [10 empty] | 2 | 60 | [9 empty] | 0
| CD | Commiunity Development | [30 empty] | 0
1 |  | Hon.Minister Dayasiri Jayasekara | Construction of cycle hut of Panduwasnuwara Divitional Education office | Karagahagedara | 1355 | 1 |  |  | 210289.62 | 200000 | 197000 | [10 empty] | 1 | 84 |  | 200000 | 3000 | 3000 | 3000 |  |  | 3000 | 2955 | 45
2 |  | Hon.Minister Dayasiri Jayasekara | Developing task of Bhikku recidance at Nallura temple | Nallura | 1356 | 1 |  |  | 402557.78 | 200000 | 197000 | [10 empty] | 1 | 400 |  | 200000 | 3000 | 3000 | 3000 |  |  | 3000 | 2955 | 45
3 |  | Hon.Minister Dayasiri Jayasekara | Compleating the remaining work of vilagedara Eksath Grama sanwardana samithiya | Karagahagedara | 1398 | 1 |  |  | 201253.1 | 200000 | 189756.12 | [10 empty] | 1 | 30 |  | 192756.12 | 3000 | 3000 | 10243.88 | 6000 | 4243.88 | 3000 | 2846.3418 | 153.6582
4 |  | Hon.Minister Dayasiri Jayasekara | Construction of Office room for Development officers of Divisional cecretary's panduwasnuwara west | Dolohomuna | 1337 | 1 |  |  | 208882.8 | 200000 | 200000 | [10 empty] | 1 | 67 |  | 200000 |  | 3000 | 0 |  |  | 3000 | 3000 | 0
5 |  | Hon.MP. Mahinda Rajapaksa | Construction Sunday school building of Diddeniya Pusparama Viharasthanya | Pallegama | 1332 | 1 |  |  | 163120.3 | 100000 | 98000 | [10 empty] | 1 | 285 |  | 99000 | 1000 | 1500 | 2000 |  |  | 1500 | 1470 | 30
6 |  | Hon.Minister Indika Bandaranayake | Constructing the building of jayasiripura rural development society | Jayasiripura | 1419 | 1 |  |  | 250000 | 200000 | 197000 | [10 empty] | 1 | 1015 |  | 200000 | 3000 | 3000 | 3000 |  |  | 3000 | 2955 | 45
7 |  | Hon.Minister Anura Priyadarshana yapa | Construction Sunday school building of Hettipola swarnagiri Viharasthanaya | Hettipola | 1336 | 1 |  |  | 215597.83 | 200000 | 197000 | [10 empty] | 1 | 1291 |  | 200000 | 3000 | 3000 | 3000 |  |  | 3000 | 2955 | 45
8 |  | Hon.Minister Indika Bandaranayake | Constructing store room of Anukkane Eksith Awamagalyadhara Samithiya | Rambewa | 1349 | 1 |  |  | 229482.49 | 200000 | 196000 | [10 empty] | 1 | 256 |  | 198000 | 2000 | 3000 | 4000 |  |  | 3000 | 2940 | 60
9 |  | Hon.Minister Indika Bandaranayake | Construction of shrine room at Gorakadeniya temple | Tekewa | 1340 | 1 |  |  | 214663.8 | 200000 | 197000 | [10 empty] | 1 | 145 |  | 200000 | 3000 | 3000 | 3000 |  |  | 3000 | 2955 | 45
10 |  | Hon.Minister Indika Bandaranayake | Construction the Damma Sala building at Pllegama Ariyawansalakara Vihara | Bandara Koswatta | 1372 | 1 |  |  | 218350.4 | 200000 | 197000 | [10 empty] | 1 | 170 |  | 200000 | 3000 | 3000 | 3000 |  |  | 3000 | 2955 | 45
11 |  | Hon. National List M.P.Navavi | Construction of a gate of Madige Midiyala Jamil Hairad Muslim Jumma Church | Madige Midiyala | 1357 | 1 |  |  | 200000 | 200000 | 197000 | [10 empty] | 1 | 2270 |  | 200000 | 3000 | 3000 | 3000 |  |  | 3000 | 2955 | 45
12 |  | Hon.Minister Dayasiri Jayasekara | Developing task of Udakadawala Rural Development society hall | Hammaliya | 1361 | 1 |  |  | 341484.11 | 200000 | 197000 | [10 empty] | 1 | 85 |  | 200000 | 3000 | 3000 | 3000 |  |  | 3000 | 2955 | 45
13 |  | Hon.Minister Indika Bandaranayake | construction a toilet system at Madaina play ground | Madaina | 1329 | 1 |  |  | 200817.65 | 200000 | 194993.25 | [10 empty] | 1 | 893 |  | 196993.25 | 2000 | 3000 | 5006.75 | 6000 | -993.25 | 3000 | 2924.8987 | 75.1013
14 |  | Hon. M.P. Thushar Indunila Amarasena | Paving interlock at ground of Govijana Sewa Madyasthanaya, Panduwasnuwara | Kadawalagedara | 1355 | 1 |  |  | 202540 | 200000 | 197000 | [10 empty] | 1 | 54000 |  | 200000 | 3000 | 3000 | 3000 |  |  | 3000 | 2955 | 45
15 |  | Hon. M.P. Thushar Indunila Amarasena | Constructing the side wall for Evoid soil erosion at ground of Kuli/ Dunukeyawaththa praimary school | Malwanegedara | 1400 | 1 |  |  | 214214.82 | 200000 | 197000 | [10 empty] | 1 | 240 |  | 199000 | 2000 | 3000 | 3000 |  |  | 3000 | 2955 | 45
16 |  | Hon. M.P. Thushar Indunila Amarasena | To renovate the office of Kuli/ Muslim M.M.V., Kotammbapitiya | Panduwasnuwara | 1346 | 1 |  |  | 203080 | 200000 | 197000 | [10 empty] | 1 | 345 |  | 199000 | 2000 | 3000 | 3000 |  |  | 3000 | 2955 | 45
17 |  | Hon. M.P. Thushar Indunila Amarasena | To rehebilitate the Toilet system at Pushparama Viharaya, Hinguregama, Halmillawewa | Hantihawa | 1423 | 1 |  |  | 53754 | 50000 | 49250 | [10 empty] | 1 | 480 |  | 50000 | 750 | 750 | 750 |  |  | 750 | 738.75 | 11.25
18 |  | Hon. M.P. Salinda Dissanayake | Constructing fence around the Ekamuthu society hall of Yayegedara Udahipanpola waththa | Yayegedara | 1370 | 1 |  |  | 45300.18 | 20000 | 19700 | [10 empty] | 1 | 35 |  | 20000 | 300 | 300 | 300 |  |  | 300 | 295.5 | 4.5
19 |  | Hon. M.P. Thushar Indunila Amarasena | For enlarging Rural developin society hall in Redeekanda, Medagama | Rideekanda | 1342 | 1 |  |  | 211285.5 | 200000 | 197000 | [10 empty] | 1 | 110 |  | 200000 | 3000 | 3000 | 3000 |  |  | 3000 | 2955 | 45
20 |  | Hon. M.P. Thushar Indunila Amarasena | Construction of Sewa piyasa for Development officers of Divisional cecretary's manduwasnuwara west | Dolohomuna | 1337 | 1 |  |  | 62192.64 | 50000 | 50000 | [10 empty] | 1 |  |  | 50000 |  | 750 |  |  |  | 750 | 750 | 0
|  | Sub Total |  |  |  | 20 |  |  | 4048867.02 | 3420000 | 3361699.37 | [10 empty] | 20 | 62201 |  |  |  |  | 0 |  | 4872.03 |  |  | 0
|  | MI | Miner Irigation | [29 empty] | 0
1 |  | Hon.Minister Indika Bandaranayake | Constructing bathin steps in Balagolla Gedaragawa tank | Mandapola | 1351 | 1 |  |  | 207035.72 | 200000 | 197000 | [10 empty] | 1 | 86 |  |  | 3000 | 3000 | 3000 |  |  | 3000 | 2955 | 45
2 |  | Hon. M.P. Thushar Indunila Amarasena | Developing task for Aluthwetiya tank in Girathalana | Girathalana | 1334 | 1 |  |  | 219435 | 200000 | 197000 | [10 empty] | 1 | 1 |  |  | 3000 | 3000 | 3000 |  |  | 3000 | 2955 | 45
3 |  | Hon. M.P. Thushar Indunila Amarasena | Renovation and to cast away soil of the Kotawewa tank in Galwewa, Thuththiripitigama, Nikawaththegama | Nallura | 1356 | 1 |  |  | 208784 | 200000 | 197000 | [10 empty] | 1 | 6 |  |  | 3000 | 3000 | 3000 |  |  | 3000 | 2955 | 45
4 |  | Hon. M.P. Thushar Indunila Amarasena | Renovation the Siyambalagaswetiya tank in Girattlana | Girathalana | 1334 | 1 |  |  | 245744 | 200000 | 197000 | [10 empty] | 1 | 1 |  |  | 3000 | 3000 | 3000 |  |  | 3000 | 2955 | 45
5 |  | Hon. M.P. Thushar Indunila Amarasena | Deepen the Siyambalagahawewa(Tank) at Morgolla | Moragolla | 1344 | 1 |  |  | 204408 | 200000 | 197000 | [10 empty] | 1 | 35 |  |  | 3000 | 3000 | 3000 |  |  | 3000 | 2955 | 45
|  | Sub Total |  |  |  | 5 |  |  | 1085406.72 | 1000000 | 985000 | [10 empty] | 5 | 129 |  |  | 65637.5 | 76387.5 |  |  |  | 76387.5 | 75043.5445 | 1343.9555
|  | SW | Social Welfare
1 |  | Hon.Minister Dayasiri Jayasekara | Supplying the loud speeker for Bamunumulla Eksath subhasadaka samithiya (wayamba/ Kuru/ Pandu/1339) | Bogolla | 1339 |  | 1 |  | 56245 | 50000 | 50000 | [10 empty] | 1 | 68 |  |  |  |  | 0 |  |  | 50000
2 |  | Hon.Minister Dayasiri Jayasekara | Supplying including Sabaragamuwa drum and cymble for Udagama, kooratihena Sri Sambuddhaloka sanday school | Udagama | 1426 |  | 1 |  | 29100 | 30000 | 29100 | [10 empty] | 1 | 125 |  |  |  |  | 900 |  |  | 29100
3 |  | Hon.Minister Dayasiri Jayasekara | Supplying instruments for named volunteer organizans of Panduwasnuwara Divionala Cecretary | common | - |  | 1 |  | 279757.05 | 280000 | 279757.05 | [10 empty] | 1 | [5 empty] | 242.95 |  |  | 279757.05
4 |  | Hon.Minister Dayasiri Jayasekara | Supplying pohoto copier for Palugahawela Kanista vidyalaya | Moragolla | 1344 |  | 1 |  | 120000 | 120000 | 120000 | [10 empty] | 1 | 70 |  |  |  |  | 0 |  |  | 120000
5 |  | Hon. M.P. Nalin Bandar Jayamaha | Supplying a saucepan set to Rathmale Paboda Welfair Society | Rathmale | 1417 |  | 1 |  | 15850 | 15000 | 15000 | [10 empty] | 1 | 25 |  |  |  |  | 0 |  |  | 15000
6 |  | Hon. M.P. Nalin Bandar Jayamaha | Supplying Instrument to Gallinda katuwa Samagi welfair society | Dolohomuna | 1337 |  | 1 |  | 14950 | 10000 | 10000 | [10 empty] | 1 | 35 |  |  |  |  | 0 |  |  | 10000
7 |  | Hon. M.P. Nalin Bandar Jayamaha | Supplying a Water tank to Nelegama Prakrama Awamngalyadhara smithiya | Karandawa | 1425 |  | 1 |  | 11000 | 7000 | 7000 | [10 empty] | 1 | 125 |  |  |  |  | 0 |  |  | 7000
8 |  | Hon. M.P. Nalin Bandar Jayamaha | Supplying Plastic chairs to Makulawewa Duivi Arauna women's society | Wadumunna | 1331 |  | 1 |  | 9965.9 | 10000 | 9965.9 | [10 empty] | 1 | 38 |  |  |  |  | 34.1 |  |  | 9965.9
9 |  | Hon.Minister Anura Priyadarshana yapa | Supplying iron cupboard for Galkanda Muditha children's home | Hettigama | 1418 |  | 1 |  | 44750 | 40000 | 40000 | [10 empty] | 1 | 45 |  |  |  |  | 0 |  |  | 40000
10 |  | Hon.Minister Anura Priyadarshana yapa | Supplying Essential goods and sport s instrument for named sport clubs and Youth's clubs | common | - |  | 1 |  | 9991.2 | 10000 | 9625 | [10 empty] | 1 | 600 |  |  |  |  | 375
11 |  | Hon.Minister Anura Priyadarshana yapa | Supplying table with umbrellas to Pradeseeya Kantha bala mandalaya for improveing self self employed productions at Panduwasnuwara west | common | - |  | 1 |  | 29030 | 30000 | 29030 | [10 empty] | 1 | 450 |  |  |  |  | 970 |  |  | 29030
12 |  | Hon.Minister Indika Bandaranayake | Supplying plate set to Kanathalawa Maranadhara Samitiya | Jayasiripura | 1419 |  | 1 |  | 20060 | 20000 | 20000 | [10 empty] | 1 | 85 |  |  |  |  | 0 |  |  | 20000
13 |  | Hon.Minister Indika Bandaranayake | Supplying a Water pump and hium pipe for Dunukeyawattha PUBUDU farmer's organization | Malwanegedara | 1400 |  | 1 |  | 124888.25 | 125000 | 124888.25 | [10 empty] | 1 | [5 empty] | 111.75
14 |  | Hon.Minister Indika Bandaranayake | supplying buffe set to Madaina Welipitiya PUBUDU awamangalyadhara Samithiya | Madaina | 1329 |  | 1 |  | 25000 | 25000 | 25000 | [10 empty] | 1 | 78 |  |  |  |  | 0 |  |  | 25000
15 |  | Hon.Minister Indika Bandaranayake | Supplying Canapi (50 × 20) to Sunandarama Vihara | Madulla | 1327 |  | 1 |  | 150000 | 150000 | 150000 | [10 empty] | 1 | 857 |  |  |  |  | 0
16 |  | Hon.Minister Indika Bandaranayake | Suppllying buffe set to Malagane SHAKTHI women's Organization | Kurundu Kumbura | 1338 |  | 1 |  | 27500 | 25000 | 25000 | [10 empty] | 1 | 35 |  |  |  |  | 0 |  |  | 25000
17 |  | Hon.Minister Indika Bandaranayake | Supplying Esteren music insturments wnd Dancing clothes set to Sunday school of Diggalagedara vihara | Diggalagedara | 1353 |  | 1 |  | 99995 | 100000 | 99995 | [10 empty] | 1 | [5 empty] | 5 |  |  | 99995
18 |  | Hon.Minister Indika Bandaranayake | Supplying instruments for Sunday schools of Sasanarakshaka bala mandalaya 1 & 2 at Panduwasnuwara AGA division | common | - |  | 1 |  |  | 100000 | 99998 | [10 empty] | 1 | [5 empty] | 2 |  |  | 46288 | 46288 | 14950
19 |  | Hon.Minister Indika Bandaranayake | Supplying buffe set to Welagedara PUBUDU women's society | Bandara Koswatta | 1372 |  | 1 |  | 28500 | 20000 | 20000 | [10 empty] | 1 | 45 |  |  |  |  | 0 |  |  | 20000
20 |  | Hon.Minister Anura Priyadarshana yapa | Supllying instrument for Bandarakoswatta Dilena Taru Youth club | Bandara Koswatta | 1372 |  | 1 |  | 10000 | 10000 | 10000 | [10 empty] | 1 | [5 empty] | 0 |  |  | 10000
21 |  | Hon. M.P. Nalin Bandar Jayamaha | Supplying Plastic chairs for wetiyegedara Mahasen Awamangalyadara samithiya | Karandawa | 1425 |  | 1 |  | 9965.9 | 10000 | 9965.9 | [10 empty] | 1 | [5 empty] | 34.1 |  |  | 9965.9
22 |  | Hon.Minister Indika Bandaranayake | Supplying Plastic chairs for Senasuma kantha Samithiya | Moragolla | 1344 |  | 1 |  | 24914.75 | 25000 | 24914.75 | [10 empty] | 1 | [5 empty] | 85.25 |  |  | 24914.75
23 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for Eksath awamangalyadhara samithiya, Jayasirigama" Dorabavila | Dorabavila | 1354 |  | 1 |  | 9965.9 | 10000 | 9965.9 | [10 empty] | 1 | [5 empty] | 34.1 |  |  | 9965.9
24 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for JANAHITHA awamangalyadhara samithiya Diggalagedara | Diggalagedara | 1353 |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | [5 empty] | 0 |  |  | 12000
25 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for SIRIPERAKUM awamangalyadhara samithiya Mandapola | Mandapola | 1351 |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | [5 empty] | 0 |  |  | 12000
26 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining set of speaker system for EKSATH rural development society, Balagolla | Mandapola | 1351 |  | 1 |  | 28500 | 25000 | 25000 | [10 empty] | 1 | [5 empty] | 0
27 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for VISAKA kanantha karya sanvidhanaya Walpaluwa, Mandapola | Othegama | 1352 |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | [5 empty] | 0 |  |  | 12000
28 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for PUBUDU sprts club, Kadawalagedara, Tuttiripitigama | Kadawalagedara | 1355 |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | [5 empty] | 0 |  |  | 12000
29 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for library of Sri Sumagalaramaya, Yayegedara, Bandarakoswattha | Yayegedara | 1370 |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | [5 empty] | 0 |  |  | 12000
30 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining instruments for Sunday school of Bl. Josaph Vaz church, Dunuk3eyawtta, Moonmaladeniya | Malawanegedara | 1400 |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | 40 |  |  |  |  | 0 |  |  | 12000
31 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for Krusi Nishpadakayange Govi samithiya, Doratiyagedara, Moonamaldeniya | Doratiyagedara | 1411 |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | 200 |  |  |  |  | 0 |  |  | 12000
32 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for Sirisangabo awamangalyadhara samithiya,Ambagahagedara | Ambagahagedeara | 1415 |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | 76 |  |  |  |  | 0 |  |  | 12000
33 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for Waishakya Pradeepa welfair society Pahala Pihimbiya, Nagollagoda | Pihimbiya | 1416 |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | 38 |  |  |  |  | 0 |  |  | 12000
34 |  | Hon. M.P. Jonston Fernando | Supplying instrument for regestered volentier societies in Panduwasnuwara west divisional secariat | common | - |  | 1 |  | 99714.6 | 100000 | 99314.7 | [10 empty] | 1 | [5 empty] | 685.3 |  |  | 40000 | 15180 | 38760 | 44134.7 | 98074.7
35 |  | Hon. M.P. Thushar Indunila Amarasena | Supplying plastic water tank for SUHADA anyoyadara samithiya Dothella, Sunandapura | Dothella | 1325 |  | 1 |  | 11000 | 8000 | 8000 | [10 empty] | 1 | 70 |  |  |  |  | 0 |  |  | 8000
36 |  | Hon. M.P. Thushar Indunila Amarasena | Supplying a sawpan set for Shakthi subhasadaka samitiya Madulla, Sunandapura | Madulla | 1327 |  | 1 |  | 10150 | 10000 | 10000 | [10 empty] | 1 | 85 |  |  |  |  | 0 |  |  | 10000
37 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for PUBUDU rural development society Ihala Malagane | Kurundu Kumbura | 1338 |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | 60 |  |  |  |  | 0 |  |  | 12000
38 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for PUBUDU EKSATH awamangalyadara samithiya Pahalgama, Thuththiripitigama | Kadawalagedara | 1355 |  | 1 |  | 9965.9 | 10000 | 9965.9 | [10 empty] | 1 | 78 |  |  |  |  | 34.1 |  |  | 9965.9
39 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining iron cup board for PANDUKABHAYA Eksath awamanglyadhara samithiya, Ambagahawewa, Hettipola | Panduwasnuwara | 1346 |  | 1 |  | 14950 | 12000 | 12000 | [10 empty] | 1 | 85 |  |  |  |  | 0 |  |  | 12000
40 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for Sri nandana awamangalyadhara, Samitiya, Meegaspitiya, Hettipola | Meegaspitiya | 1345 |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | 96 |  |  |  |  | 0 |  |  | 12000
41 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plates for PANDUWASDEW awamanglyadhara samithiya, kotambapitiya, Hettipola | Panduwasnuwara | 1346 |  | 1 |  | 9860 | 10000 | 9860 | [10 empty] | 1 | 65 |  |  |  |  | 140 |  |  | 9860
42 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plates for Sri SANGABODHI Eksath awamangalyadhara samithiya, Hipanpola, Thuththiripitigama | Kadawalagedara | 1355 |  | 1 |  | 9860 | 10000 | 9860 | [10 empty] | 1 | 84 |  |  |  |  | 140 |  |  | 9860
43 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining Sauspan set for Senasuma welfair society, Wadumunna, Kooratihena | Wadumunna | 1331 |  | 1 |  | 10150 | 10000 | 10000 | [10 empty] | 1 | 60 |  |  |  |  | 0 |  |  | 10000
44 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for SWASHAKTHI EKSATH Dansel sangamaya, Hinguruwewa, Bandarakoswaththa | Palugaswewa | 1358 |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | 58 |  |  |  |  | 0 |  |  | 12000
45 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for Sawsiri Eksath Rural Development Society, Mookalanegama, Bandarakoswaththa | Hindagahawewa | 1359 |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | 70 |  |  |  |  | 0 |  |  | 12000
46 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for Diriya Sahana welfair society, Kekunagahakotuwa | Akarawatta | 1401 |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | 68 |  |  |  |  | 0 |  |  | 12000
47 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining Sauspan set for rural development society, Akarawaththa, Moonamaladeniya | Akarawatta | 1401 |  | 1 |  | 10150 | 10000 | 10000 | [10 empty] | 1 | 85 |  |  |  |  | 0 |  |  | 10000
48 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for Diyasen awamangalyadhara samithiya Hunupolagedara, Moonamaldeniya | Ebogedara | 1409 |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | 74 |  |  |  |  | 0 |  |  | 12000
49 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining bufe set for Shakthi welfair society,Horombuwa, Moonamaldeniya | Dahanekgedara | 1413 |  | 1 |  | 22750 | 20000 | 20000 | [10 empty] | 1 | 48 |  |  |  |  | 0 |  |  | 20000
50 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plates for Jayashakthi awamangalyadhara samithiya, Kanuketigedara, Moonmaldeniya | Akarawatta | 1401 |  | 1 |  | 9860 | 10000 | 9860 | [10 empty] | 1 | 96 |  |  |  |  | 140 |  |  | 9860
51 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining Sauspan set for Siri Sugatha awamanglyadhara samithiya, Pallegama, Bandarakoswaththa | Bandara Koswatta | 1372 |  | 1 |  | 10150 | 10000 | 10000 | [10 empty] | 1 | 102 |  |  |  |  | 0 |  |  | 10000
52 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for Eksath rural development society, Kurundukumbura, Hettipola | Tekewa | 1340 |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | 60 |  |  |  |  | 0 |  |  | 12000
53 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining bufe set for Eksath awamangalyadhara samithiya, Waduwana, Hettipola | Wadumunna | 1331 |  | 1 |  | 21000 | 20000 | 20000 | [10 empty] | 1 | 98 |  |  |  |  | 0 |  |  | 20000
54 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for Eksath awamangalyadhara samithiya, Koongaswala | Ganegama | 1328 |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | 67 |  |  |  |  | 0 |  |  | 12000
55 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for Janashakti samurdhi samithiya, Hettigama | Hettigama | 1418 |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | 145 |  |  |  |  | 0 |  |  | 12000
56 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for Embogedara Awamanglyadara samithiya | Ebogedara | 1409 |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | 96 |  |  |  |  | 0 |  |  | 12000
57 |  | Hon. M.P. Thushar Indunila Amarasena | Supplying goods and instrument for women's activities organizations in divisional secretary division | common | - |  | 1 |  | 48405.8 | 50000 | 48405.8 | [10 empty] | 1 | 180 |  |  |  |  | 1594.2 |  |  | 48405.8
58 |  | Hon. M.P. Thushar Indunila Amarasena | Supplying plastic chairs for Sri sucharitha wardana Shasanarakshaka dayaka samithiya Udagama, Halmillawewa | Udagama | 1426 |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | 125 |  |  |  |  | 0 |  |  | 12000
59 |  | Hon. M.P. Thushar Indunila Amarasena | Supplying loud speeker for Eksath subasadaka samitiya, Bathalagodawewa | Bamunumulla | 1343 |  | 1 |  | 61195 | 50000 | 50000 | [10 empty] | 1 | 65 |  |  |  |  | 0 |  |  | 50000
60 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining instrument for SARANA welfair society Dematagolla, Mandapola | Diggalagedara | 1353 |  | 1 |  | 11890 | 12000 | 11760 | [10 empty] | 1 | 75 |  |  |  |  | 240 |  |  | 11760
61 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plates for PANDULA rural development society, Dorabavila, Thuththiripitigama | Dorabavila | 1354 |  | 1 |  | 9860 | 10000 | 9860 | [10 empty] | 1 | 40 |  |  |  |  | 140 |  |  | 9860
62 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for Sethsarana welfair society Jayasiripura, Nagollagoda | Jayasiripura | 1419 |  | 1 |  | 14948.85 | 15000 | 14948.85 | [10 empty] | 1 | 65 |  |  |  |  | 51.15 |  |  | 14948.85
63 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining plastic chairs for rural development society, Karambe Anukkane, Pahala Gomugomuwa | Pahala Gomugomuwa | 1396 |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | 65 |  |  |  |  | 0 |  |  | 12000
64 |  | Hon. M.P. Nalin Bandar Jayamaha | Supplyin g Plastic chairs to Kevitiya Janashakthi women's society | Kevitiya | 1422 |  | 1 |  | 9991.2 | 10000 | 9991.2 | [10 empty] | 1 | 28 |  |  |  |  | 8.8 |  |  | 9991.2
65 |  | Hon.MP. Mahinda Rajapaksa | Supplying Palastic chairs for Midiyala kantha samithiya | Midiyala | 1329 |  | 1 |  | 4982.95 | 5000 | 4982.95 | [10 empty] | 1 | 30 |  |  |  |  | 17.05 |  |  | 4982.95
66 |  | Hon. M.P. Nalin Bandar Jayamaha | Supplying Plastic chairs to Kamburapola Aruna sport club | Kamburapola | 1402 |  | 1 |  | 9965.9 | 10000 | 9965.9 | [10 empty] | 1 | 35 |  |  |  |  | 34.1 |  |  | 9965.9
67 |  | Hon.Minister Anura Priyadarshana yapa | Supplying instruments for Eksath Awamangalyadhara samithiya, Pahala Malagane in Kurundukumbura Division | Kurundu Kumbura | 1338 |  | 1 |  | 9965.9 | 10000 | 9965.9 | [10 empty] | 1 | 80 |  |  |  |  | 34.1 |  |  | 9965.9
68 |  | Hon.MP. Mahinda Rajapaksa | Supplying a buffe set for agriculture production cooperative spociety Doratiyagedara | Dorabavila | 1354 |  | 1 |  | 25500 | 20000 | 20000 | [10 empty] | 1 | 45 |  |  |  |  | 0 |  |  | 20000
69 |  | Hon.Minister Indika Bandaranayake | Supplying Plastic chairs for Akurana Ekasath Awamangalyadara Samithiya | Akurana | 1330 |  | 1 |  | 24978 | 25000 | 24978 | [10 empty] | 1 | 105 |  |  |  |  | 22 |  |  | 24978
70 |  | Hon. M.P. Thushar Indunila Amarasena | Supplying roofing sheets for Eksath Awamanglyadhara Samithiya Hettigama | Hettigama | 1418 |  | 1 |  | 14400 | 12000 | 12000 | [10 empty] | 1 | 85 |  |  |  |  | 0 |  |  |  |  | 40469.2
71 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining essential instrument for HELA BOJUNHALA, Hettipola ( This organization should be a government and Instrument Should be commmon useed) | Hettipola | 1336 |  | 1 |  | 24491.2 | 20000 | 20000 | [10 empty] | 1 | [5 empty] | 0 |  |  | 14500 | 5500
72 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining the instrument named volantier Society in Divisional secretary division | common | - |  | 1 |  | 27950 | 27000 | 27000 | [10 empty] | 1 | [5 empty] | 0
73 |  | Hon. M.P. Thushar Indunila Amarasena | Supplying Palastic chairs foe Wambatuwamulla, Pihimbiya Rthmale Awamagalyadara Samithiya | Ehetumulla | 1420 |  | 1 |  | 10677.75 | 11000 | 10677.75 | [10 empty] | 1 | 70 |  |  |  |  | 322.25 |  |  | 10677.75
74 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining Sauspan set for Janatha sanwardhana subhasadhaka samithiya, Pihimbiya, Rathmale | Rathmale |  |  | 1 |  | 12000 | 12000 | 12000 | [10 empty] | 1 | [5 empty] | 0 |  |  | 12000
75 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining Plastic chairs for Janshakthi welfair society, Barmpola, Halmillawewa | Barampola |  |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | [5 empty] | 0 |  |  | 12101.45
76 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining Plastic chairs for Awamanglyadhara samithiya Midiyala, Bandarakoswaththa | Bandarakoswaththa |  |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | [5 empty] | 0 |  |  | 12101.45
77 |  | Hon. M.P. Thushar Indunila Amarasena | Supplying Water tank for Swashakthi welfair society | Kevitiya |  |  | 1 |  | 10000 | 8000 | 8000 | [10 empty] | 1 | [5 empty] | 0
78 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining Plates for Ekamuthu welfair society Bogolla road, Hettipola | Mandapola |  |  | 1 |  | 7820 | 8000 | 7820 | [10 empty] | 1 | [5 empty] | 180
79 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining Palastic chairs for Pathibha Isuru welfair society, Hanthihawa, Halmillawewa | Hanthihawa |  |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | [5 empty] | 0 |  |  | 12101.45
80 |  | Hon.MP. Mahinda Rajapaksa | Supplying Plastic chairs for selected societies | common |  |  | 1 |  | 139522.6 | 140000 | 139522.6 | [10 empty] | 1 | [5 empty] | 477.4 |  |  | 139522.6
81 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining Plastic chairs for Pubudu Awamangalyadara samithiya Kooratihena, Welipitiya, | Madaina |  |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | [5 empty] | 0 |  |  | 12101.45
82 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining Plastic chairs for Sawsiri Rural development society Mookalanegama, Bandarakoswattha | Hindagahawewa |  |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | [5 empty] | 0 |  |  | 12101.45
83 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining Iron cup board for Samagi govi Sanvidhanaya, Kapugama, Thuththiripitigama | Nallura |  |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | [5 empty] | 0
84 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining Iron cup board for Pubudu Pre school, Kevitiya, Halmillawewa | Kevitiya |  |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | [5 empty] | 0
85 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining Sauspan set for Eksath Awamangalkyadhara samithiya, Dampitigama, Halmillawewa | Yodayakanda |  |  | 1 |  | 15400 | 15000 | 15000 | [10 empty] | 1 | [5 empty] | 0
86 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining Plastic chairs for Sahana Sewa Awamangalyadhara samithiya, Madainna | Madaina |  |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | [5 empty] | 0 |  |  | 12101.45
87 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining Plastic chairs for Janasarana Awamanglyadhara samitiya, Ambagahagedara | Ambagahagedara |  |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | [5 empty] | 0 |  |  | 12101.45
88 |  | Hon. M.P. J.C. Alawatuwala | Obtaining Plastic chairs for Gotabhaya Govisanvidhanaya, Kmburapola | Kamburapola |  |  | 1 |  | 14948.85 | 15000 | 14948.85 | [10 empty] | 1 | [5 empty] | 51.15 |  |  | 14948.85
89 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining buffe set for Eksath Awamangalyadhara samithiya | Meegaspitiya |  |  | 1 |  | 12750 | 13000 | 12750 | [10 empty] | 1 | [5 empty] | 250
90 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining Plastic chairs for Awamangalyadara samithiya, Hunnalembuwa | Dothella |  |  | 1 |  | 12101.415 | 12000 | 12000 | [10 empty] | 1 | [5 empty] | 0 |  |  | 12101.45
91 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining iron cupboard for Dilena tharu awamanglayadhara samithiya, Dangahawaththa | Kahatavila |  |  | 1 |  | 14950 | 10000 | 10000 | [10 empty] | 1 | [5 empty] | 0
92 |  | Hon. M.P. Thushar Indunila Amarasena | Supplying Palastic chairs for Eksath subasadaka samithiya, Bathalagodawewa | Bamunumulla |  |  | 1 |  | 19931.8 | 20000 | 19931.8 | [10 empty] | 1 | [5 empty] | 68.2 |  |  | 19931.8
93 |  | Hon. M.P. Thushar Indunila Amarasena | Obtaining Plastic chairs for Eksath Awamangalyadara samithiya, Uswewa | Kahatavila |  |  | 1 |  | 12101.45 | 12000 | 12000 | [10 empty] | 1 | [5 empty] | 0 |  |  | 12101.45
|  | Hon. M.P. Thushar Indunila Amarasena | Obtaining Plastic chairs for Eksath Awamangalyadara samithiya, Waduwana | Meegaspitiya |  |  | 1 |  | 14948.85 | 15000 | 14948.85 | [10 empty] | 1 | [5 empty] | 51.15 |  |  | 14948.85
|  | Sub Total |  |  |  |  | 94 |  | 2388210.465 | 2414000 | 2406524.8 | [10 empty] | 94 | 6136 |  |  |  | 152775 | 7475.2 |  |  | 1862829.9
| LD | Livelihood Development | [25 empty] | 0
Sub Total
|  | Total |  |  |  | 31 | 94 |  | 8190915.105 | 7506500 | 7409427.77 | [10 empty] | 125 | 69454 |  |  |  |  | 0 |  |  | 422732.65 | 115 | 12000
[28 empty] | 12347.23 |  |  |  | 108 | 12000
[32 empty] | 114 | 12000
[32 empty] | 125 | 12000
| ……………………………………………. |  |  |  | ……………………………………………. | [8 empty] | ……………………………………………. | [17 empty] | 74 | 48405.8
| prepared By |  |  |  | Recommended by | [8 empty] | Approved by | [17 empty] | 49 | 44134.7
[32 empty] | 101 | 10677.75
[32 empty] | 120 | 12000
[32 empty] | 111 | 12000
[9 empty] | Allocation | [22 empty] | 121 | 14948.85
[9 empty] | 63387.5 | [21 empty] | 109 | 86 | 9965.9
[9 empty] | 7443112.5 | [21 empty] | 88 | 124 | 12000
[32 empty] | 115 | 12000
[5 empty] | Expenditure | [26 empty] | 95 | 9965.9
[5 empty] | DCB |  |  |  | True Expenditure |  | 7146790.27 | [20 empty] | 119 | 12000
[9 empty] | Administrative Cost |  | 69387.5 | [20 empty] | 113 | 139522.6
[25 empty] | t | [7 empty] | 385621.5
[5 empty] | National List |  |  |  | True Expenditure |  | 194000
[9 empty] | Administrative Cost |  | 3000
7413177.77
[9 empty] | Remaining |  | 3750
[5 empty] | Final |  |  |  | Total Expenditure |  | 7409427.77

## Sheet2
Decentralized Capital Budget Programme - 2017 - (With Nitonal list)
Pysical and Financial Progress as /2017/12/31
Summary Report Construction
Name of the DS Division :- Panduwasnuwara West
S.No |  | Name of MP | Total(contruction) Project | Total Estimate Cost (Rs.) |  | Allocation (Rs) | Expenditure (with Administrative Cost) | Physical Progress | [9 empty] | No of Beneficiariesz
[8 empty] | Estimates are being/to be prepared | Estimate Approved bid document prepared | Qutation/ Bid Called | Qutation/ Bid Received | Contract Awarded | 26 - 40% | 41 - 60% | 61 - 80% | 81 - 99% | 100%
|  |  |  | With VAT | Witout VAT |  |  | A | B1 | B2 | B3 | B4
1 | WS | Rural Water supply | 1 |  | 99797.42 | 100000 | 97890.7 | [9 empty] | 1 | 35
2 | EL | Rural Electrisity | 3 |  | 68319.6 | 72500 | 67812.9 | [9 empty] | 3 | 893
3 | RA | Rural Access | 2 |  | 500313.88 | 500000 | 490500 | [9 empty] | 2 | 60
4 | EI | Economic Infrastructure
5 | RW | Rural Welfare
6 | CD | Commiunity Development | 20 |  | 4048867.02 | 3420000 | 3361699.37 | [9 empty] | 20 | 62201
7 | MI | Miner Irigation | 5 |  | 1085406.72 | 1000000 | 985000 | [9 empty] | 5 | 129
8 | SW | Social Welfare
9 | SS | Social Services
10 | CP | Commiunity Protection
11 | LD | Livelihood Development
12 | RE | Rural Economy
|  | Total | 31 |  | 5802704.64 | 5092500 | 5002902.97 | [9 empty] | 31 | 62330
| ……………………………………………. |  |  |  |  | ……………………………………………. |  |  |  |  | …………………………………………….
| prepared By |  |  |  |  | Recommended by |  |  |  |  | Approved by

## Sheet3
Decentralized Capital Budget Programme - 2017 - (With Nitonal list)
Pysical and Financial Progress as /2017/12/31
Summary Report (Goods/Services/Purchase)
Name of the DS Division :- Panduwasnuwara West
S.No |  | Name of MP | Total(contruction) Project | Total Estimate Cost (Rs.) |  | Allocation (Rs) | Expenditure (with Administrative Cost) | Physical Progress | [9 empty] | No of Beneficiariesz
[8 empty] | Estimates are being/to be prepared | Estimate Approved bid document prepared | Qutation/ Bid Called | Qutation/ Bid Received | Contract Awarded | 26 - 40% | 41 - 60% | 61 - 80% | 81 - 99% | 100%
|  |  |  | With VAT | Witout VAT |  |  | A | B1 | B2 | B3 | B4
1 | WS | Rural Water supply
2 | EL | Rural Electrisity
3 | RA | Rural Access
4 | EI | Economic Infrastructure
5 | RW | Rural Welfare
6 | CD | Commiunity Development
7 | MI | Miner Irigation
8 | SW | Social Welfare | 94 |  | 2388210.47 | 2414000 | 2406524.8 | [9 empty] | 94 | 6136
9 | SS | Social Services
10 | CP | Commiunity Protection
11 | LD | Livelihood Development
12 | RE | Rural Economy
|  | Total | 94 |  | 2388210.47 | 2414000 | 2406524.8 | [9 empty] | 94 | 6136
| ……………………………………………. |  |  |  |  | ……………………………………………. |  |  | ` |  | …………………………………………….
| prepared By |  |  |  |  | Recommended by |  |  |  |  | Approved by